## RFQ Template
stage | deliverable | required | owner | evidence | status | due_date | risk_level | escalation_trigger | notes
Sample Gate | Released drawing revision | Yes | Engineering | Drawing revision record | Not Started | 2026-05-10 | High | No released revision by gate date
Sample Gate | Critical specification list | Yes | Engineering | Spec sheet attached | Not Started | 2026-05-10 | High | Missing critical limits
Sample Gate | Initial dimensional check result | Yes | Quality | Inspection report | Not Started | 2026-05-12 | Medium | Out-of-limit trend observed
Sample Gate | Initial magnetic performance check | Yes | Quality | Magnetic check report | Not Started | 2026-05-12 | High | Demag risk signal unresolved
Sample Gate | Sample packaging confirmation | Yes | Supply Chain | Packaging spec approval | Not Started | 2026-05-12 | Medium | Damage risk not contained
Pilot Gate | Control plan issued | Yes | Quality | Control plan document | Not Started | 2026-06-05 | High | Control plan not approved
Pilot Gate | Traceability field mapping | Yes | Quality | Lot traceability template | Not Started | 2026-06-05 | High | Lot fields incomplete
Pilot Gate | Process capability evidence | Yes | Engineering | Capability summary | Not Started | 2026-06-08 | High | Cpk trend below threshold
Pilot Gate | Incoming inspection alignment | Yes | Quality | IQC checklist agreement | Not Started | 2026-06-08 | Medium | Incoming criteria mismatch
Pilot Gate | Pilot shipment packaging validation | Yes | Supply Chain | Pilot pack test result | Not Started | 2026-06-10 | Medium | Transit damage risk unresolved
Pilot Gate | Pilot quantity and cadence lock | Yes | Program | Pilot release plan | Not Started | 2026-06-10 | Medium | Customer milestone mismatch
SOP Gate | Mass-production shipment criteria | Yes | Quality | Shipment acceptance standard | Not Started | 2026-07-15 | High | No signed shipment criteria
SOP Gate | Label and carton marking standard | Yes | Supply Chain | Labeling spec | Not Started | 2026-07-15 | Medium | Labeling mismatch risk
SOP Gate | Export document package lock | Yes | Supply Chain | Document checklist | Not Started | 2026-07-15 | Medium | Customs document gap
SOP Gate | Deviation classification matrix | Yes | Quality | Deviation matrix v1.0 | Not Started | 2026-07-18 | High | Stop-ship criteria undefined
SOP Gate | Escalation contact matrix | Yes | Program | Escalation contact list | Not Started | 2026-07-18 | High | No owner reachable within SLA
SOP Gate | Containment SLA definition | Yes | Quality | SLA statement | Not Started | 2026-07-18 | High | Containment response >24h
SOP Gate | Customer communication template | Yes | Program | Approved message template | Not Started | 2026-07-20 | Medium | Schedule-impact event without template
Ramp 30/60/90 | Day 30 issue closure review | Yes | Program | Review minutes | Not Started | 2026-08-01 | Medium | Open critical issues remain
Ramp 30/60/90 | Day 60 yield and CAPA review | Yes | Quality | Yield/CAPA report | Not Started | 2026-08-31 | Medium | CAPA closure cycle too long
Ramp 30/60/90 | Day 90 shipment stability review | Yes | Supply Chain | OTD and quality summary | Not Started | 2026-09-30 | Medium | Shipment stability below target
Sign-off | Engineering sign-off | Yes | Engineering | Signature/date | Not Started | 2026-07-20 | High | Gate approved without engineering sign-off
Sign-off | Quality sign-off | Yes | Quality | Signature/date | Not Started | 2026-07-20 | High | Gate approved without quality sign-off
Sign-off | Program sign-off | Yes | Program | Signature/date | Not Started | 2026-07-20 | High | Gate approved without program sign-off